## Report
Sr No | Engineer Name | Engineer Code | Schedule Date | Vertical | Category | Project Manager | Call Number | Store Code | Store Name | City | State | Store Format | Visit Type | Problem | Status | Comment | Schedule Date | Call Date | SM Name | Zone
1 | Dhananjay Patil | PPRR01167804 | 2026-07-20 | Retail | NSO | Rajkumar Pramanick | 8034 | 8034 | CINE MALL | VADODARA | GUJARAT | RELIANCE TRENDS | Project | NSO | WIP |  | 2026-07-20 |  | Vinay Mishra | West
2 | Dhananjay Patil | PPRR01167804 | 2026-07-22 | Retail | Absent | Rajkumar Pramanick | Absent | NOSTORE | NA | VADODARA | GUJARAT |  | Absent | Due To Personal Reasone | Pending | Shubham Sir Change the Schedule | 2026-07-22 |  | Vinay Mishra | West
3 | Dhananjay Patil | PPRR01167804 | 2026-07-22 | Retail | FIRE ALARM SYSTEM | Rajkumar Pramanick | SD63358177 | T2TL | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Service | SMOKE DETECTORS SHOWING CONTINUOUS RED LIGHT | Spare Required | One Loopcard Faulty And Validate By Kaushik Sir | 2026-07-22 | 2026-07-13 | Vinay Mishra | West
4 | Dhananjay Patil | PPRR01167804 | 2026-07-22 | Retail | NSO | Rajkumar Pramanick | 8034 | 8034 | VADODARA | VADODARA | GUJARAT | RELIANCE TRENDS | Project | NSO | WIP | Camera Installation WIP | 2026-07-22 |  | Vinay Mishra | West
5 | Dhananjay Patil | PPRR01167804 | 2026-07-23 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD62488424 | 8873 | VADODARA | VADODARA | GUJARAT | RELIANCE DIGITAL | Service | DVR IP Not Ping - 10.108.60.130 - 20260514_172744 | Visit Pending |  | 2026-07-23 | 2026-07-22 | Vinay Mishra | West
6 | Dhananjay Patil | PPRR01167804 | 2026-07-23 | Retail | PA SYSTEM | Rajkumar Pramanick | SD63500639 | FREB | 7 SEAS MALL | VADODARA | GUJARAT | SMARTBAZAAR | Service | AMPLIFIER NOT POWERING ON | WIP | Fuse Issue | 2026-07-23 | 2026-07-22 | Vinay Mishra | West
7 | Dhananjay Patil | PPRR01167804 | 2026-07-23 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63493969 | T2TL | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Service | 10.113.53.215 CCTV camera shows a live view but the DVR is not recording or playback shows no recor... | Visit Pending |  | 2026-07-23 | 2026-07-22 | Vinay Mishra | West
8 | Dhananjay Patil | PPRR01167804 | 2026-07-23 | Retail | EAS SYSTEM | Rajkumar Pramanick | SD63490801 | 8645 | VADODARA | VADODARA | GUJARAT | JIO STORE | Service | Near SLP Desk left side -1 & right side-2 three EAS Antenna not working properly | Spare Required | 2 24 VLT Adaopter Faulty | 2026-07-23 | 2026-07-22 | Vinay Mishra | West
9 | Dhananjay Patil | PPRR01167804 | 2026-07-24 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD62488424 | 8873 | VADODARA | VADODARA | GUJARAT | RELIANCE DIGITAL | Service | DVR IP Not Ping - 10.108.60.130 - 20260514_172744 | Pending | High Impedance Ballon Connector Required | 2026-07-24 | 2026-07-22 | Vinay Mishra | West
10 | Dhananjay Patil | PPRR01167804 | 2026-07-24 | Retail | PA SYSTEM | Rajkumar Pramanick | SD63500639 | FREB | 7 SEAS MALL | VADODARA | GUJARAT | SMARTBAZAAR | Service | AMPLIFIER NOT POWERING ON | Visit Pending |  | 2026-07-24 | 2026-07-22 | Vinay Mishra | West
11 | Dhananjay Patil | PPRR01167804 | 2026-07-24 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63493969 | T2TL | VERAVAL | VADODARA | GUJARAT | RELIANCE SMART | Service | 10.113.53.215 CCTV camera shows a live view but the DVR is not recording or playback shows no recor... | Visit Pending |  | 2026-07-24 | 2026-07-22 | Vinay Mishra | West
12 | Dhananjay Patil | PPRR01167804 | 2026-07-24 | Retail | NSO | Rajkumar Pramanick | 8034 | 8034 | CINE MALL | VADODARA | GUJARAT | RELIANCE TRENDS | Project | NSO | WIP | Store WIP | 2026-07-24 |  | Vinay Mishra | West
13 | Dhananjay Patil | PPRR01167804 | 2026-07-25 | Retail | PA SYSTEM | Rajkumar Pramanick | SD63500639 | FREB | 7 SEAS MALL | VADODARA | GUJARAT | SMARTBAZAAR | Service | AMPLIFIER NOT POWERING ON | Spare required | Amplifire Validate By Kaushik Sir | 2026-07-25 | 2026-07-22 | Vinay Mishra | West
14 | Dhananjay Patil | PPRR01167804 | 2026-07-25 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63493969 | T2TL | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Service | 10.113.53.215 CCTV camera shows a live view but the DVR is not recording or playback shows no recor... | Visit pending |  | 2026-07-25 | 2026-07-22 | Vinay Mishra | West
15 | Dhananjay Patil | PPRR01167804 | 2026-07-25 | Retail | DFMD/HHMD | Rajkumar Pramanick | SD63434650 | M018 | AIMS MALL | VADODARA | GUJARAT | MALL MANAGEMENT | Service | HHMD Continues beeping - not function properly | Completed |  | 2026-07-25 | 2026-07-18 | Vinay Mishra | West
16 | Dhananjay Patil | PPRR01167804 | 2026-07-25 | Retail | MAIL BY SC | Rajkumar Pramanick | 5725 | 5725 | AIMS MALL | VADODARA | GUJARAT | RELIANCE JEWALES | Special project | Material Need to Check And Inform To Kaushik Sir | Completed |  | 2026-07-25 |  | Vinay Mishra | West
17 | Dhananjay Patil | PPRR01167804 | 2026-07-26 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63493969 | T2TL | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Service | 10.113.53.215 CCTV camera shows a live view but the DVR is not recording or playback shows no recor... | Completed |  | 2026-07-26 | 2026-07-22 | Vinay Mishra | West
18 | Dhananjay Patil | PPRR01167804 | 2026-07-26 | Retail | PA SYSTEM | Rajkumar Pramanick | SD63500553 | TP74 | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Service | MUSIC SYSTEM ISSUE ¦ amplifier not working | Completed |  | 2026-07-26 | 2026-07-22 | Vinay Mishra | West
19 | Dhananjay Patil | PPRR01167804 | 2026-07-26 | Retail | INTRUSION DETECTION SYSTEM | Rajkumar Pramanick | SD63540853 | 3560 | VADODARA | VADODARA | GUJARAT | JIO STORE | Service | From Last tow days every night call from RRSOC PIR is active but checked the cctv inside its normal ... | Visit pending |  | 2026-07-26 | 2026-07-25 | Vinay Mishra | West
20 | Dhananjay Patil | PPRR01167804 | 2026-07-26 | Retail | PMS | Rajkumar Pramanick | 7928 | 7928 | VADODARA | VADODARA | GUJARAT | JIO STORE | Service | PMS NEED TO BE COMPLETED | Completed |  | 2026-07-26 |  | Vinay Mishra | West
21 | Dhananjay Patil | PPRR01167804 | 2026-07-27 | Jio Business | CCTV SYSTEM | Anuj Mukhne | SD34388261 | I-GJ-SAVL-ILA-0001 | SAVLI | VADODARA | GUJARAT | ILA | Service | Camera Offline need to Check With Laptop | Revisit |  | 2026-07-27 | 2026-07-26 | Vinay Mishra | West
22 | Dhananjay Patil | PPRR01167804 | 2026-07-27 | Jio Business | CCTV SYSTEM | Anuj Mukhne | SD34388265 | I-GJ-SAVL-ENB-9020 | SAVLI | VADODARA | GUJARAT | ENB | Service | 10.113.53.215 CCTV camera shows a live view but the DVR is not recording or playback shows no recor... | Revisit |  | 2026-07-27 | 2026-07-26 | Vinay Mishra | West
23 | Dhananjay Patil | PPRR01167804 | 2026-07-28 | Retail | PMS | Rajkumar Pramanick | M018 | M018 | AIMS MALL | VADODARA | GUJARAT | MALL MANAGEMENT | PMS | Complet PMS Activity And Confirm With PMS Team | Visit pending |  | 2026-07-28 |  | Vinay Mishra | West
24 | Dhananjay Patil | PPRR01167804 | 2026-07-28 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63564851 | THG5 | VADODARA | VADODARA | GUJARAT | HAMLEYS TOYS | Service | video fast forward required | Completed |  | 2026-07-28 | 2026-07-27 | Vinay Mishra | West
25 | Dhananjay Patil | PPRR01167804 | 2026-07-28 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD59671008 | THG5 | VADODARA | VADODARA | GUJARAT | HAMLEYS TOYS | Service | Recording & Playback Issue | Completed |  | 2026-07-28 |  | Vinay Mishra | West
26 | Dhananjay Patil | PPRR01167804 | 2026-07-28 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD60720925 | THG5 | VADODARA | VADODARA | GUJARAT | HAMLEYS TOYS | Service | Recording & Playback Issue | Completed |  | 2026-07-28 |  | Vinay Mishra | West
27 | Dhananjay Patil | PPRR01167804 | 2026-07-28 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD59604091 | THG5 | VADODARA | VADODARA | GUJARAT | HAMLEYS TOYS | Service | CCTV Monitor broken | Spare required | Moniter requier Validate By Samir Sir | 2026-07-28 |  | Vinay Mishra | West
28 | Dhananjay Patil | PPRR01167804 | 2026-07-28 | Retail | EAS SYATEM | Rajkumar Pramanick | SD63490801 | 8645 | VADODARA | VADODARA | GUJARAT | JIO STORE | Service | Near SLP Desk left side -1 & right side-2 three EAS Antenna not working properly | Completed | ADEPTER PURCHESE | 2026-07-28 | 2026-07-22 | Vinay Mishra | West
29 | Dhananjay Patil | PPRR01167804 | 2026-07-29 | External | FAS Project | Prasad Kasar | THA2 | THA2 | VADODARA | VADODARA | GUJARAT | RELIANCE TRENDS | Special project | FIRE Tube Installation Project At Mornig Time 8 AM To 10:30 AM | Completed | With Drill | 2026-07-29 |  | Vinay Mishra | West
30 | Dhananjay Patil | PPRR01167804 | 2026-07-29 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63583919 | T1KG | PETLAD | VADODARA | GUJARAT | RELIANCE SMART | Service | 01 CAMARA VIEW NOT CLEAR/BLUR IMAGE ¦ null ¦ IP : 10.95.199.7 | Visit pending |  | 2026-07-29 | 2026-07-28 | Vinay Mishra | West
31 | Dhananjay Patil | PPRR01167804 | 2026-07-29 | Retail | FAS SYSTEM | Rajkumar Pramanick | SD63582545 | M018 | VADODARA | VADODARA | GUJARAT | MALL MANAGEMENT | Service | Fire Alarm in start condition - 20260728_153822 | Completed |  | 2026-07-29 | 2026-07-28 | Vinay Mishra | West
32 | Dhananjay Patil | PPRR01167804 | 2026-07-29 | Retail | PMS | Rajkumar Pramanick | M018 | M018 | AIMS MALL | VADODARA | GUJARAT | MALL MANAGEMENT | PMS | Complet PMS Activity And Confirm With PMS Team | WIP |  | 2026-07-29 |  | Vinay Mishra | West
33 | Dhananjay Patil | PPRR01167804 | 2026-07-30 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63582864 | TX8H | ANAND | VADODARA | GUJARAT | RELIANCE TRENDS | Service | Dear Team, ¦ null ¦ At site TX8H All camera Live view not opened . ¦ IP : 10.99.41.131 | Completed |  | 2026-07-30 | 2026-07-28 | Vinay Mishra | West
34 | Dhananjay Patil | PPRR01167804 | 2026-07-30 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63583919 | T1KG | PETLAD | VADODARA | GUJARAT | RELIANCE SMART | Service | 01 CAMARA VIEW NOT CLEAR/BLUR IMAGE ¦ null ¦ IP : 10.95.199.7 | Completed |  | 2026-07-30 | 2026-07-28 | Vinay Mishra | West
35 | Dhananjay Patil | PPRR01167804 | 2026-07-31 | Retail | PMS | Rajkumar Pramanick | M018 | M018 | AIMS MALL | VADODARA | GUJARAT | MALL MANAGEMENT | PMS | Complet PMS Activity And Confirm With PMS Team | Visit Pending |  | 2026-07-31 |  | Vinay Mishra | West
36 | Dhananjay Patil | PPRR01167804 | 2026-07-31 | Retail | IFAS SYSTEM | Rajkumar Pramanick | SD63614452 | TBQD | VADODARA | VADODARA | GUJARAT | FASHION FACTORY | Service | false alarm generated | Visit Pending |  | 2026-07-31 | 2026-07-30 | Vinay Mishra | West
37 | Dhananjay Patil | PPRR01167804 | 2026-07-31 | Retail | IFAS SYSTEM | Rajkumar Pramanick | SD63415575 | 3579 | VADODARA | VADODARA | GUJARAT | JIO STORE | Service | Sounder is active randomly in day time which is faulty kindly resolve the issue. | Completed |  | 2026-07-31 | 2026-07-16 | Vinay Mishra | West
38 | Dhananjay Patil | PPRR01167804 | 2026-07-31 | Retail | Hoto Report | Rajkumar Pramanick | 3560 | 3560 | KARELI BAUHG | VADODARA | GUJARAT | JIO STORE | HOTO | Hoto Report Need To Sign up | Completed |  | 2026-07-31 |  | Vinay Mishra | West
39 | Dhananjay Patil | PPRR01167804 | 2026-08-01 | Retail | PMS | Rajkumar Pramanick | M018 | M018 | AIMS MALL | VADODARA | GUJARAT | MALL MANAGEMENT | PMS | Complet PMS Activity And Confirm With PMS Team | Completed |  | 2026-08-01 |  | Vinay Mishra | West
40 | Dhananjay Patil | PPRR01167804 | 2026-08-01 | Retail | IFAS SYSTEM | Rajkumar Pramanick | SD63614452 | TBQD | VADODARA | VADODARA | GUJARAT | FASHION FACTORY | Service | false alarm generated | Revisit | PIR Configration Pending | 2026-08-01 | 2026-07-30 | Vinay Mishra | West
41 | Dhananjay Patil | PPRR01167804 | 2026-08-02 | Retail | FAS SYSTEM | Rajkumar Pramanick | SD63628385 | M018 | VADODARA | VADODARA | GUJARAT | MALL MANAGEMENT | Service | Fire Alarm in start condition - 20260731_170850 | Revisit | With One More Engineer | 2026-08-02 |  | Vinay Mishra | West
42 | Dhananjay Patil | PPRR01167804 | 2026-08-03 | Brands | PMS | Rajkumar Pramanick | TO56 | TO56 | INORBIT MALL | VADODARA | GUJARAT | Superdry | PMS | Complet PMS Activity And Confirm With PMS Team | Completed |  | 2026-08-03 |  | Vinay Mishra | West
43 | Dhananjay Patil | PPRR01167804 | 2026-08-03 | Brands | PMS | Rajkumar Pramanick | TZVL | TZVL | INORBIT MALL | VADODARA | GUJARAT | Ritu Kumar | PMS | Complet PMS Activity And Confirm With PMS Team | Visit pending |  | 2026-08-03 |  | Vinay Mishra | West
44 | Dhananjay Patil | PPRR01167804 | 2026-08-03 | Brands | PMS | Rajkumar Pramanick | TA8H | TA8H | INORBIT MALL | VADODARA | GUJARAT | Sunglass Hut | PMS | Complet PMS Activity And Confirm With PMS Team | Visit pending |  | 2026-08-03 |  | Vinay Mishra | West
45 | Dhananjay Patil | PPRR01167804 | 2026-08-03 | Retail | MAIL BY SC | Rajkumar Pramanick | M018 | M018 | VADODARA | VADODARA | GUJARAT | MALL MANAGEMENT | Material Movement | Need To Collcat Materil From Jewales Store And Handover to M018 Store | Completed |  | 2026-08-03 |  | Vinay Mishra | West
46 | Dhananjay Patil | PPRR01167804 | 2026-08-03 | RIL | CCTV SYSTEM | Rajkumar Pramanick | SD63655857 | TE0G | VADODARA | VADODARA | GUJARAT | JIOMART-CENTRO | Service | 10.108.78.198 . found time not match ...one camera blur | Completed |  | 2026-08-03 | 2026-08-02 | Vinay Mishra | West
47 | Dhananjay Patil | PPRR01167804 | 2026-08-04 | Brands | PMS | Rajkumar Pramanick | TZVL | TZVL | INORBIT MALL | VADODARA | GUJARAT | Ritu Kumar | PMS | Complet PMS Activity And Confirm With PMS Team | Completed |  | 2026-08-04 |  | Vinay Mishra | West
48 | Dhananjay Patil | PPRR01167804 | 2026-08-04 | Brands | PMS | Rajkumar Pramanick | TA8H | TA8H | INORBIT MALL | VADODARA | GUJARAT | Sunglass Hut | PMS | Complet PMS Activity And Confirm With PMS Team | Completed |  | 2026-08-04 |  | Vinay Mishra | West
49 | Dhananjay Patil | PPRR01167804 | 2026-08-04 | Retail | MAIL BY SC | Rajkumar Pramanick | M018 | M018 | VADODARA | VADODARA | GUJARAT | MALL MANAGEMENT | Special project | SD Need To Installed | WIP |  | 2026-08-04 |  | Vinay Mishra | West
50 | Dhananjay Patil | PPRR01167804 | 2026-08-05 | External | FAS Project | Prasad Kasar | TNP1 | TNP1 | ANKLESWER | VADODARA | GUJARAT | RELIANCE TRENDS | Special project | FIRE Tube Installation Project At Mornig Time 8 AM To 12:30 PM | Completed | With Drill Machine | 2026-08-05 |  | Vinay Mishra | West
51 | Dhananjay Patil | PPRR01167804 | 2026-08-06 | Jio Business | CCTV SYSTEM | Anuj Mukhne | SD34468232 | I-GJ-KRJN-ENB-9005 | VADODARA | VADODARA | GUJARAT | ENB | Service | I-GJ-KRJN-ENB-9005 - Camera Offline | Visit pending |  | 2026-08-06 | 2026-08-05 | Vinay Mishra | West
52 | Dhananjay Patil | PPRR01167804 | 2026-08-06 | Retail | PMS | Rajkumar Pramanick | 6790 | 6790 | VADODARA | VADODARA | GUJARAT | DxMini | PMS | PMS Need To Be Completed | Completed |  | 2026-08-06 |  | Vinay Mishra | West
53 | Dhananjay Patil | PPRR01167804 | 2026-08-07 | Retail | FIRE ALARM SYSTEM | Rajkumar Pramanick | SD63725325 | M018 | VADODARA | VADODARA | GUJARAT | MALL MANAGEMENT | Service | SD is not blinking on Ground floor near by Jio Mart electric panel room. | Pending | SD Loop Need to Check | 2026-08-07 | 2026-08-06 | Vinay Mishra | West
54 | Dhananjay Patil | PPRR01167804 | 2026-08-07 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63721272 | TE0G | VADODARA | VADODARA | GUJARAT | JIOMART-CENTRO | Service | http://10.108.78.198/doc/page/main.asp camera no..15 not clear image... ¦ http://10.108.78.196/doc... | Completed |  | 2026-08-07 | 2026-08-06 | Vinay Mishra | West
55 | Dhananjay Patil | PPRR01167804 | 2026-08-07 | Retail | MAIL BY SC | Rajkumar Pramanick | FRDZ | FRDZ | INORBIT MALL | VADODARA | GUJARAT | RELIANCE SMART | Special project | Camera Relocation Need to Done And Inform to Kaushik Sir | Pending | Camera Relocation Poll Reqiured | 2026-08-07 |  | Vinay Mishra | West
56 | Dhananjay Patil | PPRR01167804 | 2026-08-07 | Retail | MAIL BY SC | Rajkumar Pramanick | 6723 | 6723 | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Special project | Camera Relocation Need to Done And Inform to Kaushik Sir | Visit pending |  | 2026-08-07 |  | Vinay Mishra | West
57 | Dhananjay Patil | PPRR01167804 | 2026-08-08 | Retail | IFAS SYSTEM | Rajkumar Pramanick | SD63740975 | 7998 | VADODARA | VADODARA | GUJARAT | JIO STORE | Service | Sounder is not functional. | Completed |  | 2026-08-08 | 2026-08-07 | Vinay Mishra | West
58 | Dhananjay Patil | PPRR01167804 | 2026-08-08 | Retail | FAS SYSTEM | Rajkumar Pramanick | SD63725325 | M018 | AIMS MALL | VADODARA | GUJARAT | MALL MANAGEMENT | Service | SD is not blinking on Ground floor near by Jio Mart electric panel room. | Completed |  | 2026-08-08 | 2026-08-06 | Vinay Mishra | West
59 | Dhananjay Patil | PPRR01167804 | 2026-08-08 | Retail | MAIL BY SC | Rajkumar Pramanick | 6723 | 6723 | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Special project | Camera Relocation Need to Done And Inform to Kaushik Sir | Visit pending |  | 2026-08-08 |  | Vinay Mishra | West
60 | Dhananjay Patil | PPRR01167804 | 2026-08-09 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63746591 | TE0G | VADODARA | VADODARA | GUJARAT | JIOMART-CENTRO | Service | http://10.108.78.200/doc/page/preview.asp all camera found RECORDING NOT HAPPENING... | Pending | RRSOC Team Not Responding | 2026-08-09 | 2026-08-08 | Vinay Mishra | West
61 | Dhananjay Patil | PPRR01167804 | 2026-08-09 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63481263 | TE0G | VADODARA | VADODARA | GUJARAT | JIOMART-CENTRO | Service | CAMERA SMPS Recived Need to Install | Completed |  | 2026-08-09 | 2026-07-31 | Vinay Mishra | West
62 | Dhananjay Patil | PPRR01167804 | 2026-08-09 | Retail | PMS | Rajkumar Pramanick | TE0G | TE0G | VADODARA | VADODARA | GUJARAT | JIOMART-CENTRO | PMS | Complet PMS Activity And Confirm With PMS Team | WIP | Tagging And Naming WIP | 2026-08-09 |  | Vinay Mishra | West
63 | Dhananjay Patil | PPRR01167804 | 2026-08-10 | Retail | Week Off | Rajkumar Pramanick | Week Off | NOSTORE |  | VADODARA | GUJARAT |  | Week Off | Week off adjust | Week Off |  | 2026-08-10 |  | Vinay Mishra | West
64 | Dhananjay Patil | PPRR01167804 | 2026-08-11 | Retail | FAS SYSTEM | Rajkumar Pramanick | SD63773989 | M018 | VADODARA | VADODARA | GUJARAT | MALL MANAGEMENT | Service | SD 26 loop no.02 found faulty its showing continuous red light. | Completed |  | 2026-08-11 | 2026-08-10 | Vinay Mishra | West
65 | Dhananjay Patil | PPRR01167804 | 2026-08-11 | Retail | EAS SYATEM | Rajkumar Pramanick | SD63771765 | T2TL | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Service | ANTENNA NOT DETECTING THE TAGS | Visit pending |  | 2026-08-11 | 2026-08-09 | Vinay Mishra | West
66 | Dhananjay Patil | PPRR01167804 | 2026-08-11 | Retail | PMS | Rajkumar Pramanick | 5725 | 5725 | VADODARA | VADODARA | GUJARAT | RELIANCE JEWALES | PMS | PMS NEED TO BE COMPLETED | Completed |  | 2026-08-11 |  | Vinay Mishra | West
67 | Dhananjay Patil | PPRR01167804 | 2026-08-12 | Retail | EAS SYSTEM | Rajkumar Pramanick | SD63771765 | T2TL | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | Service | ANTENNA NOT DETECTING THE TAGS | Spare required | EAS Antena Validate By Kaushik Sir | 2026-08-12 | 2026-08-09 | Vinay Mishra | West
68 | Dhananjay Patil | PPRR01167804 | 2026-08-12 | Retail | PMS | Rajkumar Pramanick | 6712 | 6712 | VADODARA | VADODARA | GUJARAT | RELIANCE SMART | PMS | PMS NEED TO BE COMPLETED | Completed |  | 2026-08-12 |  | Vinay Mishra | West
69 | Dhananjay Patil | PPRR01167804 | 2026-08-13 | Retail | FAS SYSTEM | Rajkumar Pramanick | SD63803030 | FRDZ | VADODARA | VADODARA | GUJARAT | SMARTBAZAAR | Service | SMOKE DETECTOR CONTINUES BEEPING | Completed |  | 2026-08-13 | 2026-08-12 | Vinay Mishra | West
70 | Dhananjay Patil | PPRR01167804 | 2026-08-13 | Retail | PMS |  | 492 | 492 | VADODARA | VADODARA | GUJARAT | Clovia | PMS | PMS NEED TO BE COMPLETED | Completed |  | 2026-08-13 |  | Vinay Mishra | West
71 | Dhananjay Patil | PPRR01167804 | 2026-08-14 | Brands | PMS | Rajkumar Pramanick | THG5 | THG5 | VADODARA | VADODARA | GUJARAT | HAMLYES TOYS | PMS | FAS Penal Lugs Need to Install And Complet The PMS | Completed |  | 2026-08-14 |  | Vinay Mishra | West
72 | Dhananjay Patil | PPRR01167804 | 2026-08-14 | Retail | NSO | Rajkumar Pramanick | 8034 | 8034 | CINE MALL | VADODARA | GUJARAT | RELIANCE TRENDS | Project | NSO | Visit pending |  | 2026-08-14 |  | Vinay Mishra | West
73 | Dhananjay Patil | PPRR01167804 | 2026-08-14 | Retail | FAS SYSTEM | Rajkumar Pramanick | SD63725325 | M018 | AIMS MALL | GODHRA | GUJARAT | MALL MANAGEMENT | Service | Need to Install 20 MTR Cable For Fire Loop | Completed |  | 2026-08-14 | 2026-08-06 | Vinay Mishra | West
74 | Dhananjay Patil | PPRR01167804 | 2026-08-14 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63829808 | M018 | AIMS MALL | GODHRA | GUJARAT | MALL MANAGEMENT | PMS | 10.108.77.97 / 10.108.94.145 CH 2 / CH1 SHOWING NVS | Completed |  | 2026-08-14 | 2026-08-06 | Vinay Mishra | West
75 | Dhananjay Patil | PPRR01167804 | 2026-08-15 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63837930 | 6712 | VADODARA | VADODARA | GUJARAT | RELIANCE | Service | IP NOT PINGING ¦ 10.108.58.101 | Completed |  | 2026-08-15 | 2026-08-14 | Vinay Mishra | West
76 | Dhananjay Patil | PPRR01167804 | 2026-08-16 | Retail | Week off | Rajkumar Pramanick | Week off | NOSTORE |  | VADODARA | GUJARAT |  | Week Off | No Movement | Week Off |  | 2026-08-16 |  | Vinay Mishra | West
77 | Dhananjay Patil | PPRR01167804 | 2026-08-17 | Retail | PMS | Rajkumar Pramanick | FRDV | FRDV | SHALIMAR | VADODARA | GUJARAT | RELIANCE SMART | PMS | Complet PMS Activity And Confirm With PMS Team | WIP |  | 2026-08-17 |  | Vinay Mishra | West
78 | Dhananjay Patil | PPRR01167804 | 2026-08-18 | Jio Business | CCTV SYSTEM | Anuj Mukhne | SD34567984 | I-GJ-KRJN-ENB-9005 | VADODARA | VADODARA | GUJARAT | ENB | Service | I-GJ-KRJN-ENB-9005 - Camera Offline | Visit pending | With Laptop | 2026-08-18 | 2026-08-17 | Vinay Mishra | West
79 | Dhananjay Patil | PPRR01167804 | 2026-08-18 | Retail | CCTV SYSTEM | Rajkumar Pramanick | SD63870459 | TE0G | VADODARA | ANAND | GUJARAT | JIOMART-CENTRO | Service | http://10.108.78.198/doc/page/main.asp found camera no.01 damaged , camera no. 05 no video signal ,... | Completed |  | 2026-08-18 | 2026-08-17 | Vinay Mishra | West
80 | Dhananjay Patil | PPRR01167804 | 2026-08-18 | Jio Business | CCTV SYSTEM | Anuj Mukhne | SD34565439 | I-GJ-SAVL-ENB-9039 | SAVLI | GODHRA | GUJARAT | ENB | Service | Camera Offline Need to Check With Laptop | Completed | With Laptop | 2026-08-18 | 2026-08-06 | Vinay Mishra | West
81 | Dhananjay Patil | PPRR01167804 | 2026-08-19 | Retail | PMS | Rajkumar Pramanick | FRDV | FRDV | SHALIMAR | VADODARA | GUJARAT | RELIANCE SMART | PMS | Complet PMS Activity And Confirm With PMS Team | WIP | Tagging And Naming WIP | 2026-08-19 |  | Vinay Mishra | West
82 | Dhananjay Patil | PPRR01167804 | 2026-08-20 | Retail | PMS | Rajkumar Pramanick | FRDV | FRDV | SHALIMAR | VADODARA | GUJARAT | RELIANCE SMART | PMS | Complet PMS Activity And Confirm With PMS Team | WIP |  | 2026-08-20 |  | Vinay Mishra | West
83 | Dhananjay Patil | PPRR01167804 | 2026-08-21 | Retail | PMS | Rajkumar Pramanick | FRDV | FRDV | SHALIMAR | VADODARA | GUJARAT | RELIANCE SMART | PMS | Complet PMS Activity And Confirm With PMS Team |  |  | 2026-08-21 |  | Vinay Mishra | West